## Cover
Scrum Reporting Form
| Day | 2023-04-19
| Due Date | 2023-04-20
| Team Name: | TUI Bros
| Team Members: | John, Eli
| Project: | file-o-saurus-rex
Division of Labor
| Module Name | Author
| tui.cpp | John | canceled
| files.cpp | Eli | canceled
| settings.cpp | TBD | canceled
You have had an opportunity to decide on a project and start the general set-up for the project. The next step is to go through and identify all the tasks that need to be commpleted to have a finished product for the Final Project Presentation. The Fibonacci Sequence to assign importance of each task. Rate the tasks by the importance of when they need to be done as well as the importance to the completion of the project. Some tasks with a low priority may never be completed. Those can be saved for a later project. Come back to this list each day, mark tasks that have been completed as "Done" and repriotize the remaining tasks.
| Plans for | 2023-04-20
| Team Member | Tasks planned | Prriority
| All | Decide on Project | 1
| All | Identify major parts of the project | 2
| All | Set up GitHub account and invite all participants | 3
| Story behind your project | Do you ever open the Windows file explorer and think "Mannnn this sucks". ME TOO (on windows 11). So, instead of sitting around and complaining we are going to make a file manager for the terminal, wooo. Will it be better than the Windows 11 File Explorer, no, but it will be useful. You will be able to traverse directories, delete and create files/directories, save favorites in a side menu, and maybe even open files (if there is time). Together, we will take down the Windows File Explorer (not really).

## 20 Apr
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-04-20 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-04-21
| Team Name: | TUI Bros
| Team Members: | John, Eli
| Project: | mite
Division of Labor
| Module Name | Author
| command.cpp | John Eli
| edit.cpp | John Eli
| File.cpp | John Eli
| lsp.cpp | John Eli
| main.cpp | John Eli
| screen.cpp | John Eli
| Tasks Due | 2023-04-20 | Prriority
| Team Member | Tasks planned
| All | Decide on Project | Done
| All | Identify major parts of the project | Done
| All | Set up GitHub account and invite all participants | Done
| All | Finish scrum cover | Done
| Plans for | 2023-04-21
| Team Member | Tasks planned
| All | Break up project into modules (use UML diagrams) | 1
| TBA | To Be Determined | ?
| TBA | To Be Determined | ?

## 21 Apr
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-04-20 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-04-23
| Team Name: | TUI Bros
| Team Members: | John, Eli
| Project: | file-o-saurus-rex
Division of Labor
| Module Name | Author
| command.cpp | John
| edit.cpp | Eli
| File.cpp | TBD
| lsp.cpp | TBD
main.cpp
screen.cpp
| Tasks Due | 2023-04-20 | Prriority
| Team Member | Tasks planned
| All | Break up project into modules (use UML diagrams) | #NAME? | done
| John | Proper loading of files | 10 | done
| Eli | Split files into array | 9 | done
| Plans for | 2023-04-23
| Team Member | Tasks planned
| John | Unbuffered IO | 9
| Eli | Windows unbuffered IO | 5

## 24 Apr
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-04-23 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-04-24
| Team Name: | TUI Bros
| Team Members: | John, Eli
| Project: | mite
Division of Labor
| Module Name | Author
| command.cpp | John
| edit.cpp | Eli
| File.cpp | TBD
lsp.cpp
main.cpp
screen.cpp
| Tasks Due | 2023-04-23 | Prriority
| Team Member | Tasks planned
| John | Linux unbuffered IO | 9 | done
| Eli | Windows unbuffered IO | 5
| John | convert to CMake | 4
| Plans for | 2023-04-24
| Team Member | Tasks planned
| TBA | To Be Determined | ?
| TBA | To Be Determined | ?
| TBA | To Be Determined | ?

## 25 Apr
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-04-24 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-04-25
| Team Name: | TUI Bros
| Team Members: | John, Eli
| Project: | mite
Division of Labor
| Module Name | Author
| command.cpp | John
| edit.cpp | Eli
| File.cpp | TBD
lsp.cpp
main.cpp
screen.cpp
| Tasks Due | 2023-04-24 | Prriority
| Team Member | Tasks planned
| Eli | Split lines at newline | 1 | done
| Eli | Delete lines at beginning | 3 | done
| John | ESC goes back to normal mode | 5 | done
| Plans for | 2023-04-25
| Team Member | Tasks planned
| John | fix minimal bulid |  | convert to cmake first

## 26 Apr
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-04-25 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-04-26
| Team Name: | TUI Bros
| Team Members: | John, Eli
| Project: | file-o-saurus-rex
Division of Labor
| Module Name | Author
| command.cpp | John
| edit.cpp | Eli
| File.cpp | TBD
lsp.cpp
main.cpp
screen.cpp
| Tasks Due | 2023-04-25 | Prriority
| Team Member | Tasks planned
| John | Undo across multiple lines
| Plans for | 2023-04-26
| Team Member | Tasks planned

## 27 Apr
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-04-26 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-04-27
| Team Name: | TUI Bros
| Team Members: | John, Eli
| Project: | file-o-saurus-rex
Division of Labor
| Module Name | Author
| command.cpp | John
| edit.cpp | Eli
| File.cpp | TBD
lsp.cpp
main.cpp
screen.cpp
| Tasks Due | 2023-04-26 | Prriority
| Team Member | Tasks planned
| Plans for | 2023-04-27
| Team Member | Tasks planned for Project Presentration

## 28 Apr
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-04-27 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-04-30
| Team Name: | TUI Bros
| Team Members: | John, Eli
| Project: | file-o-saurus-rex
Division of Labor
| Module Name | Author
| command.cpp | John
| edit.cpp | Eli
| File.cpp | TBD
lsp.cpp
main.cpp
screen.cpp
| Tasks Due | 2023-04-27 | Prriority
| Team Member | Tasks planned
| Plans for | 2023-04-30
| Team Member | Tasks planned for Project Presentration

## 1 May
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-04-30 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-05-01
| Team Name: | TUI Bros
| Team Members: | John, Eli
| Project: | file-o-saurus-rex
Division of Labor
| Module Name | Author
| command.cpp | John
| edit.cpp | Eli
| File.cpp | TBD
lsp.cpp
main.cpp
screen.cpp
| Tasks Due | 2023-04-30 | Prriority
| Team Member | Tasks planned
| Plans for | 2023-05-01
| Team Member | Tasks planned for Project Presentration

## 2 May
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-05-01 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-05-02
| Team Name: | TUI Bros
| Team Members: | John, Eli
| Project: | file-o-saurus-rex
Division of Labor
| Module Name | Author
| command.cpp | John
| edit.cpp | Eli
| File.cpp | TBD
lsp.cpp
main.cpp
screen.cpp
| Tasks Due | 2023-05-01 | Prriority
| Team Member | Tasks planned
| Plans for | 2023-05-02
| Team Member | Tasks planned for Project Presentration

## 3 May
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-05-02 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-05-03
| Team Name: | TUI Bros
| Team Members: | John, Eli
| Project: | file-o-saurus-rex
Division of Labor
| Module Name | Author
| command.cpp | John
| edit.cpp | Eli
| File.cpp | TBD
lsp.cpp
main.cpp
screen.cpp
| Tasks Due | 2023-05-02 | Prriority
| Team Member | Tasks planned
| Plans for | 2023-05-03
| Team Member | Tasks planned for Project Presentration

## 4 May
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-05-03 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-05-04
| Team Name: | Mouse Detective
| Team Name: | TUI Bros
| Team Members: | John, Eli
| Project: | file-o-saurus-rex
Division of Labor
| Module Name | Author
| command.cpp | John
| edit.cpp | Eli
| File.cpp | TBD
lsp.cpp
main.cpp
screen.cpp
| Tasks Due | 2023-05-03 | Prriority
| Team Member | Tasks planned
| Plans for | 2023-05-04
| Team Member | Tasks planned for Project Presentration

## 5 May
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-05-04 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-05-07
| Team Name: | TUI Bros
| Team Members: | John, Eli
| Project: | file-o-saurus-rex
Division of Labor
| Module Name | Author
| command.cpp | John
| edit.cpp | Eli
| File.cpp | TBD
lsp.cpp
main.cpp
screen.cpp
| Tasks Due | 2023-05-04 | Prriority
| Team Member | Tasks planned
| Plans for | 2023-05-07
| Team Member | Tasks planned for Project Presentration

## Final
Scrum Reporting Form |  |  | Priority | Status | Final Thoughts on this Process
| Day | 2023-05-07 |  | Either DONE or what problem needs to be solved before the task can be completed. | This page is the last Scrum Form due and is to record your final thoughts on the process
| Due Day | Today
| Team Name: | TUI Bros
| Team Members: | John, Eli
| Project: | file-o-saurus-rex
Division of Labor
| Module Name | Author
| tui.cpp | John
| files.cpp | Eli
| settings.cpp | TBD
| Tasks Due | 2023-05-07
| Team Member | Presentaion | Prriority
|  | Present slide show and program deminstration | 1
| Plans for | Today
| Team Member | Tasks planned
None - complete